## Sheet1
No | No
WPID | Category
WPID Actual | SOW
Program | Status
SOW Detail Implementation | Assignment Date
Need / No Need Survey | PIC
Project | Assignment
SOW | Action
Site ID Original | Project
SITE ID | Cost Center
SITE NAME | Site ID
Cluster | SITE NAME
REGION | REGION
LOL Date | ZONE
Survey Site Existing | IOM/BA No.
Finish Survey | Kab.
Status Survey | H3I Technical Branch
Create TSSR | Address
Create SID | LONG
TSSR.pdf Submit/Upload Date to PPM | LAT
SID.pdf Submit/Upload Date to PPM | To.Co ID
Upload TSSR.pdf to Point Drive Date | To.Co NAME
Upload SID.pdf to Point Drive Date | SLA End Date
Upload / submit Foto Survey to Point Drive Date | SLA End Date Review
Upload Summary TSSR | SLA End Year Review
Status Doc. Survey | SLA End Month
Backlog Doc. Survey | RFI Actual
Status RFI | New Toco
RFI Notification | ID Toco
PO Survey Number | Site Name
PO Released | Site Address
PO Survey Amount | Longitude
PO NY Released | Latitude
PO Survey Estimate Amount | Tower Type
MOS | Tower Height
NY MOS | Ant. Height
Installation Start | PIC To.CO
Installation Finish | History Candidat
Plan Integration | Detail SOW New TSS
Integration Actual | Link Info
OA | Diameter Info
Full OA | Survey Loss Actual
Partial OA | TSSR Loss Submit
MOS, Installation, and Integration Remarks | TSSR Loss Approved
Backlog Implementasi | Colo Remove Submit
Milestone Implementasi | Colo Removed App.
OG Install | Colo New Submit
Need Dismantle | Colo New Approved
Dismantle Date | Link. Dism. Actual
Dismantle Done | Link. Dism. Done
Create ATF | Start Reroute
Submit ATF | Finish Reroute
Approval ATF | Blocking Reroute
ATP On Site | ATP Actual
ATP Remote | ATP Pass
Create Doc ATP | PR Submit NE
Upload to PPM BOQ.PDF | PR App. NE
Upload to PPM ATF.xls | PR Submit FE
Upload to PPM Redline .pdf | PR App. FE
Upload ABD .dwg | ATP & BAST Submit
Upload to PPM ABD.pdf | ATP & BAST App.
Upload LLD/NDB | SAAF Submit
Upload ATP Functional | SAAF Approved
Upload ATP Physical | MSFI Submit
Upload to Pointdrive BoQ .pdf | MSFI Approved
Upload to Point Drive ATF.xls | Milestone Reroute Link
Upload to Point Drive ATP.xls/.pdf | Blocking Doc.
Upload to Point Drive Redline .pdf | BOQ Submit
Upload ABD.pdf to Point Drive | BOQ App.
Upload Photo ATP to Point Drive | Boq Value
Upload SA to IPM | PO Number
Upload HS to IPM | % Re - Route
Status SA dan HS | Survey Date
Take Data NetGear | Survey Submit
Take Data NetGear Status | Colo Revisi Submit
ATP Doc Submit | Colo Revisi Approved
ATP Reject | Verification Start
ATP Approved | Verification Finish
Status Doc ATP | Rectification Start
PO TI Number | Rectification Finish
PO TI Released | Activity
PO TI Amount | Detail Activity
PO TI NY Released | Blocking Rectification
PO TI Estimate Amount | ATP Onsite
NI_GAP Analysis | ATP Pass
Dependency | PR Submit
STATUS ASSIGNMENT TI | PR Approved
WCC Survey Submit | ATF Submit
WCC Survey Submit Amount | ATF Approved
WCC Survey Approved | BAST & Doc ATP Submit
WCC Survey Amount Approved | BAST & Doc ATP App.
Gap Wcc Survey Submit and Approved | SAAF Submit
WCC TIS Submit | SAAF Approved
WCC TIS Submit Amount | Milestone Rectification
WCC TIS Approved | Blocking Doc.
WCC TIS Approved Amount | BOQ Submit
Gap Wcc TIS Submit and Approved | BOQ App.
Grand Total | % Misplace
JR Actual
Report Submit
Report App
Blocking JR
BAST Submit
BAST Approved
Milsetone JR
Blocking Doc.
BOQ Submit
BOQ Value
BOQ Approved
PO JR Number
PO JR Value
% JR
Survey New RNP
Survey FE Loss
Detail FE ID
Diam. Antena
Blocking TSS
TSSR New RNP Submit
TSSR New RNP App.
TSSR FE Loss Submit
TSSR FE Loss App.
New Colo Submit to TP
New Colo App. H3I
Remarks & Blocking TSSR
SAAF Submit
SAAF App.
BAST TSSR Submit
BAST TSSR App.
MSFI Submit
MSFI App.
FAC Submit
FAC App.
Milestone TSSR
Blocking Doc. Completion
BOQ Submit 1
BOQ Submit 2
BOQ App. 1
BOQ App. 2
BOQ Value
PO TSS Number 1
PO TSS Number 2
PO TSS 1 Value
PO TSS 2 Value
PR Submit
PR Approved
GRN
% TSSR
IP Release
APD Submit to TP
APD App. H3I
BOQ Submit to H3I
BOQ App. H3I
CME Start Blocking
BOQ Sign by Commercial
CME Start
Additional Cost
Actual PLN Connection
CME Finish
Actual RFI
ATP Actual
ATP Pass
ATP Doc & BAST Submit
ATP Doc & BAST App.
MSFI Submit
MSFI Approved
PAC Submit
PAC Approved
FAC Submit
FAC Approved
Milestone Mini CME
BOQ Submit
BOQ App.
BOQ Value
PO Mini CME
PO Mini CME Value
GRN 100% Actual
Invoice 100%
% Mini CME
NE Colo Removed Submit
NE Colo Removed App.
NE Dism. Actual
NE Dism. Done
Blcoking Dismantle
NE PR Submit TP/H3I
NE PR App. TP/H3I
FE ID
FE Colo Removed/Revisi Submit
FE Colo Removed/Revisi App.
FE Dism. Actual
FE Dism. Done
FE PR Submit TP/H3I
FE PR App. TP/H3I
Blocking Dismantle
Bongkar Rampung Actual
BA Bongkar Rampung Closed
Blocking Bongkar Rampung
Dism. Tray
Dism. Pole/BOX KWH
Dism. Pole/BOX ACPDB
Fluidic/Genset Dismantle
Additional Cost
Material On Temporary Storage
Material Dism. Location
APM Delivery to WH Cibarusah
Material Inbound WH H3I
Aging On Temporary Storage
ATF Submit
ATF Approved
BAST & Doc. Dism. Submit
BAST & Doc. Dism. App.
PAC Submit
PAC Approved
Par 1 Submit
Par 1 Approved
FAC Submit
FAC Approved
BOQ Submit
BOQ App.
BOQ Value
PO Dismantle Only
PO Dismantle Only Value
GRN 25% Actual
Invoice 25%
GRN 60% Actual
Invoice 60%
GRN 15% Actual
Invoice 15%
% Dismantle Only
Actual Mos
Installl Start
Installl Finish
Add Cost Actual
Blocking Rebuilt
Install Fluidic/Genset
ATP Fluidic/Genset
RFS
OA
ATP Actual
ATP Pass
Site Unblock
Blocking Unblock
PR New Submit
PR New App.
Blocking Document Submit
Doc. ATP, BAST Submit & FAC
Doc. ATP, BAST & FAC App.
MSFI Submit
MSFI Approved
PAC Submit
PAC Approved
Milestone Re - Installation
Milestone Dismantle + Re - Installation
Priority
BOQ Submit
BOQ App.
BOQ Value
PO Rebuild Only
PO Rebuild Value
GRN 25% Actual
Invoice 25%
GRN 60% Actual
Invoice 60%
GRN 15% Actual
Invoice 15%
% Rebuild Only
PO Dism. + Rebuild
PO Dism. + Rebuild Value
GRN 25% Actual
Invoice 25%
GRN 60% Actual
Invoice 60%
GRN 15% Actual
Invoice 15%
% Dism. + Rebuild
Start Work
Finish Work
Add Cost Value
Add Cost Remark
Boq Submit
Boq Approved
% Add Cost

## Sheet2
H3I Direct | ISAT
Cancel | ASSIGNMENT TAKE OVER
Dismantle Only | Installation Only
Dismantle + Re - Installation | NEED KONFIRM NOKIA
Justification Survey | Survey + Installasi
Mini CME | Survey + Installasi + cross connect TDM
Mobilization | Survey + Installasi + Dismantle
Rectification UE | SURVEY ONLY
Re - Installation
Reroute Link
TSS

## Sheet3
Add 2100 | (NULL,'Add 2100'),
Add LTE 15 MHz | (NULL,'Add LTE 15 MHz'),
Add U900 | (NULL,'Add U900'),
New LTE 15 MHz | (NULL,'New LTE 15 MHz'),
New LTE 15 MHz + Add U900 | (NULL,'New LTE 15 MHz + Add U900'),
NEW SITE | (NULL,'NEW SITE'),
New Site G/U900 & L1800 | (NULL,'New Site G/U900 & L1800'),
paket Abis | (NULL,'paket Abis'),
UG BW 15 MHz | (NULL,'UG BW 15 MHz'),

## Sheet6
Change Transport + Packet abis / No Program / No Program / No Program / No Program | (NULL,'Change Transport + Packet abis / No Program / No Program / No Program / No Program'),
G900/U900 (333/111) | (NULL,'G900/U900 (333/111)'),
G900/U900/L1800 15 Mhz 4x4 MIMO/L2100 5 Mhz | (NULL,'G900/U900/L1800 15 Mhz 4x4 MIMO/L2100 5 Mhz'),
Modernization G900 / No Program / No Program / New U900 / No Porgram | (NULL,'Modernization G900 / No Program / No Program / New U900 / No Porgram'),
Modernization GSM / No Program / No Program / New U900 / New L1800 15 Mhz | (NULL,'Modernization GSM / No Program / No Program / New U900 / New L1800 15 Mhz'),
Modernization GSM + Packet Abis / No Program / No Program / New U900 / New L1800 15 Mhz | (NULL,'Modernization GSM + Packet Abis / No Program / No Program / New U900 / New L1800 15 Mhz'),
Modernization GSM + Packet abis / No Program / No Program / New U900 / No Program | (NULL,'Modernization GSM + Packet abis / No Program / No Program / New U900 / No Program'),
Modernization RRU + Downgrade TRX / Modernization DCS + Downgrade TRX / No Program / New U900 / New L1800 15 mhz | (NULL,'Modernization RRU + Downgrade TRX / Modernization DCS + Downgrade TRX / No Program / New U900 / New L1800 15 mhz'),
Modernization RRU + Downgrade TRX / No Program / No Program / New U900 / New L1800 15 Mhz | (NULL,'Modernization RRU + Downgrade TRX / No Program / No Program / New U900 / New L1800 15 Mhz'),
Modernization RRU / Modernization RRU / No Program / New U900 / New L1800 15 Mhz | (NULL,'Modernization RRU / Modernization RRU / No Program / New U900 / New L1800 15 Mhz'),
Modernization RRU / No Program / No Program / New U900 / New L1800 15 Mhz | (NULL,'Modernization RRU / No Program / No Program / New U900 / New L1800 15 Mhz'),
Modernization RRU / No Program / No Program / New U900 / No Program | (NULL,'Modernization RRU / No Program / No Program / New U900 / No Program'),
Modernization RRU + Packet Abis / No Program / No Program / New U900 / New L1800 15 Mhz | (NULL,'Modernization RRU + Packet Abis / No Program / No Program / New U900 / New L1800 15 Mhz'),
New G900/-/-/New U900/- | (NULL,'New G900/-/-/New U900/-'),
New G900/-/-/New U900/New L1800 15 Mhz 4x4 MIMO/New L2100 5 Mhz | (NULL,'New G900/-/-/New U900/New L1800 15 Mhz 4x4 MIMO/New L2100 5 Mhz'),
New G900 / No Program / New U2100 / New U900 / New L1800 15 Mhz | (NULL,'New G900 / No Program / New U2100 / New U900 / New L1800 15 Mhz'),
New G900 / No Program / No Program / New U900 / New L1800 15 Mhz 4x4 MIMO / New L2100 5 Mhz | (NULL,'New G900 / No Program / No Program / New U900 / New L1800 15 Mhz 4x4 MIMO / New L2100 5 Mhz'),
New G900 / No Program / No Program / New U900 / No Program | (NULL,'New G900 / No Program / No Program / New U900 / No Program'),
New Site G/U900 & L1800 | (NULL,'New Site G/U900 & L1800'),
No Program / Modernization DCS & Downgrade TRX / No Program / No Program / New L1800 15 Mhz | (NULL,'No Program / Modernization DCS & Downgrade TRX / No Program / No Program / New L1800 15 Mhz'),
No Program / Modernization DCS / No Program / No Program / New L1800 15 Mhz | (NULL,'No Program / Modernization DCS / No Program / No Program / New L1800 15 Mhz'),
No Program / Modernization DCS / No Program / No Program / Upgrade L1800 15 Mhz | (NULL,'No Program / Modernization DCS / No Program / No Program / Upgrade L1800 15 Mhz'),
No Program / No Program / No Program / No Program / New L1800 15 Mhz | (NULL,'No Program / No Program / No Program / No Program / New L1800 15 Mhz'),
No Program / No Program / No Program / No Program / upgrade L1800 to 15 Mhz | (NULL,'No Program / No Program / No Program / No Program / upgrade L1800 to 15 Mhz'),
No Program / Split BCF / No Program / No Program / New L1800 15 Mhz | (NULL,'No Program / Split BCF / No Program / No Program / New L1800 15 Mhz'),
Out doorization + Downgrade TRX / No Program / No Program / New U900 / New L1800 15 Mhz | (NULL,'Out doorization + Downgrade TRX / No Program / No Program / New U900 / New L1800 15 Mhz'),
Outdoorization / No Program / No Program / New U900 / No Program | (NULL,'Outdoorization / No Program / No Program / New U900 / No Program'),
Packet Abis / Modernization DCS + Packet Abis / No Program / No Program / New L1800 15 Mhz | (NULL,'Packet Abis / Modernization DCS + Packet Abis / No Program / No Program / New L1800 15 Mhz'),
Packet Abis / No Program / New U2100 / No Program / No Program | (NULL,'Packet Abis / No Program / New U2100 / No Program / No Program'),
Packet Abis / No Program / No Program / New U900 / No Program | (NULL,'Packet Abis / No Program / No Program / New U900 / No Program'),
Packet Abis / No Program / No Program / No Program / New L1800 15 Mhz | (NULL,'Packet Abis / No Program / No Program / No Program / New L1800 15 Mhz'),
Packet Abis / No Program / No Program / No Program / No Program | (NULL,'Packet Abis / No Program / No Program / No Program / No Program'),
Packet Abis / Packet Abis / No Program / No Program / New L1800 15 Mhz | (NULL,'Packet Abis / Packet Abis / No Program / No Program / New L1800 15 Mhz'),
Packet Abis / Packet Abis / No Program / No Program / upgrade L1800 to 15 Mhz | (NULL,'Packet Abis / Packet Abis / No Program / No Program / upgrade L1800 to 15 Mhz'),
Packet Abis / Split BCF + Packet Abis / No Program / No Program / New L1800 15 Mhz | (NULL,'Packet Abis / Split BCF + Packet Abis / No Program / No Program / New L1800 15 Mhz');

## Sheet9
New site | (NULL,'New site'),
Overlay Capacity | (NULL,'Overlay Capacity'),
Overlay IBS | (NULL,'Overlay IBS'),
Overlay RED | (NULL,'Overlay RED'),
Overlay yellow | (NULL,'Overlay yellow'),